## Bug Tracker
Bug ID | Severity | Area | Issue | Location (console logs-location) | Root Cause | How to Resolve
BUG-001 | Critical | Auth / Password Reset | Forgot-password endpoint returns the working reset token in the API response body. | placeonix-hub-backend/src/controllers/authController.js:174 (forgotPassword) | When SMTP is not configured (current prod state — no SMTP_HOST/SMTP_PASS set), the code returns resetToken directly in the JSON response instead of only emailing it. | Remove resetToken from the response entirely in any environment where NODE_ENV==='production'. Either block forgot-password from working until SMTP is configured, or send the token only via a verified email channel. Never return it in-band once SMTP is live.
BUG-002 | Critical | Leads / CRM (public endpoint) | Public, unauthenticated lead-creation endpoint allows mass assignment of internal fields. | placeonix-hub-backend/src/controllers/leadController.js:8-15; routes/leadRoutes.js:10-20 (POST /leads) | Validator only checks firstName/lastName/email/phone, but the full req.body is passed into Lead.create(), so an anonymous caller can also set status, assignedTo, source, etc. | Explicitly whitelist the fields accepted from public input: build the Lead.create() payload as {firstName,lastName,email,phone,message} only — never spread req.body directly for a public route.
BUG-003 | Critical | Payments | Student-facing fee payment is fully simulated with no gateway verification. | placeonix-hub-backend/src/controllers/paymentController.js:7-51 (payMyFees) | A 'completed' Payment record and enrollment fee update are created purely from client-submitted amount/method — there is no Razorpay/Stripe call, no signature verification, no external source of truth. | Integrate a real payment gateway (Razorpay/Stripe) with server-side signature verification before marking a payment 'completed'. Until integrated, this flow must not be exposed for real money — restrict to admin-recorded manual payments only, clearly labeled as such in the UI.
BUG-004 | Critical | Payments | Admin payment-update endpoint accepts arbitrary status/amount changes with no verification. | placeonix-hub-backend/src/controllers/paymentController.js:137-140 (updatePayment) | Raw req.body (including status, amount, transactionId) is forwarded directly into findByIdAndUpdate with no gateway cross-check. | Restrict which fields updatePayment can change (e.g. notes/reason only); require any status transition to 'completed'/'refunded' to be backed by a verified gateway reference, and log an audit entry (who/when/why) for every change.
BUG-005 | Critical | Mock Interviews | Any student can view another student's private interview feedback and scores. | placeonix-hub-backend/src/controllers/mockInterviewController.js:22 | An unconditional 'if (req.query.student) filter.student = req.query.student;' runs AFTER the role-based self-scoping, so a student can override their own scope by passing ?student=<otherId>. | Remove the unconditional query-param override for the student role. Only allow the student filter to be set from req.user._id for students; only admins/mentors may filter by an arbitrary student id.
BUG-006 | Critical | File Uploads / Infrastructure | Uploaded files (avatars, documents, submissions) will not persist in production. | placeonix-hub-backend/src/services/uploadService.js:9-38; vercel.json (serverless deploy) | Multer writes to local disk / /tmp. Vercel serverless functions have ephemeral, per-invocation filesystems, so any file written by one invocation is gone by the next — files silently disappear. | Replace disk storage with an object-storage backend (S3, Cloudinary, or Vercel Blob) using a multer storage engine (e.g. multer-s3) or direct SDK upload from the upload controller. Must be fixed before file-upload features can be trusted in production.
BUG-007 | High | Sessions (ownership) | Any mentor can start, complete, edit, or delete another mentor's session. | placeonix-hub-backend/src/controllers/sessionController.js (create/update/delete/start/complete); routes/sessionRoutes.js:12-17 | authorize('mentor','admin') checks role only; nothing verifies the acting mentor equals the session's instructor field. | Add an ownership check in each handler: if (req.user.role==='mentor' && String(session.instructor) !== String(req.user._id)) return 403. Apply to update, delete, start, complete.
BUG-008 | High | Assignments (ownership) | Any mentor can edit or delete another mentor's assignment. | placeonix-hub-backend/src/controllers/assignmentController.js:75-90 (updateAssignment, deleteAssignment) | No check that the mentor teaches the assignment's batch before allowing PATCH/DELETE by id. | Look up the assignment's batch, confirm batch.mentor === req.user._id (or role==='admin') before allowing the write; return 403 otherwise.
BUG-009 | High | Assignments (grading, ownership) | Any mentor/admin-role account can grade any student's submission on any assignment, not just their own batch's. | placeonix-hub-backend/src/controllers/assignmentController.js:136-168 (reviewSubmission) | No check that the reviewing mentor is assigned to the assignment's batch. | Same ownership check as BUG-008, applied before writing the score/feedback to the submission subdocument.
BUG-010 | High | Join Requests (ownership) | Any mentor can approve, reject, or set the meeting link on another mentor's join requests. | placeonix-hub-backend/src/controllers/joinRequestController.js:44-55 (update) | The mentor-role PATCH handler never checks request.mentor === req.user._id before mutating status/meetingLink. | Add: if (req.user.role==='mentor' && String(request.mentor) !== String(req.user._id)) return 403, before allowing the update.
BUG-011 | High | Mock Interviews (ownership) | Any mentor can edit or delete another mentor's mock-interview feedback. | placeonix-hub-backend/src/controllers/mockInterviewController.js:54-89 (updateMock, deleteMock) | No check that mock.interviewer === req.user._id before allowing PATCH/DELETE. | Add the same ownership check pattern as BUG-007/008/010 before permitting the write.
BUG-012 | High | Users | Any authenticated student can fetch any other user's full profile document. | placeonix-hub-backend/src/routes/userRoutes.js:35 (GET /users/:id) | Route has no ownership or role guard — protect() only confirms the caller is logged in, not that they may view this specific user. | Apply ownerOrAdmin('id') middleware (already exists in middleware/auth.js) to this route, or restrict to authorize('admin','mentor') plus an ownership check for self.
BUG-013 | High | Payments (unscoped read) | Any mentor can list every student's payment records. | placeonix-hub-backend/src/routes/paymentRoutes.js:10 (GET /payments) | listPayments has no authorize() restriction at the route level; scoping is only partially handled inside the controller for role==='student'. | Add authorize('admin') to the route (or explicitly scope the mentor case in-controller to only the students in the mentor's own batches).
BUG-014 | High | Certificates (unscoped read) | Any mentor can list all students' certificates. | placeonix-hub-backend/src/routes/certificateRoutes.js:12 (GET /certificates) | listCertificates has no authorize() restriction at the route level. | Add authorize('admin') to the route, or scope to the mentor's own students only if mentor access is intentionally required.
BUG-015 | High | Reviews | Any authenticated user can inflate a review's 'helpful' count with repeated requests. | placeonix-hub-backend/src/controllers/reviewController.js:90-98 (markHelpful) | No per-user tracking of who has already marked a review helpful — the counter simply increments on every call. | Track marks in a helpfulBy: [ObjectId] array on the Review model (or a separate join collection) and only increment + push if req.user._id is not already present.
BUG-016 | High | Frontend / Announcements — Stored XSS | Announcement title/body rendered via unescaped innerHTML on the student dashboard. | frontend/placeonix-hub-portal.html:2123 | a.title / a.body are concatenated directly into an HTML string instead of passed through the existing escHtml() helper. | Wrap both fields in escHtml() (already defined and used correctly elsewhere in the file, e.g. line 1532) before insertion.
BUG-017 | High | Frontend / Announcements — Stored XSS | Announcement title/body rendered unescaped in the admin/mentor announcement list. | frontend/placeonix-hub-portal.html:2963-2966 (renderAnnouncements) | Same pattern as BUG-016 — raw string concatenation instead of escHtml(). | Apply escHtml() to a.title and a.body at this render site.
BUG-018 | High | Frontend / Notifications — Stored XSS | Notification title/message rendered unescaped in the notification panel. | frontend/placeonix-hub-portal.html:4235-4236 (openNotifications) | n.title / n.message inserted into innerHTML without escaping. | Apply escHtml() to both fields before rendering.
BUG-019 | High | Frontend / Session & Course Cards — Stored XSS | Session titles and course titles rendered unescaped across multiple card renderers. | frontend/placeonix-hub-portal.html: classCard (1993), liveClassCard (2336), recordingCard (2348), inPersonCard (2355), scheduleRow (2404), renderSessions (3542), courseCardPremium (2272), renderMyLearning (2483) | These renderers insert s.title / c.title raw, inconsistent with escHtml() usage elsewhere in the same file. | Apply escHtml() to every title field at each of these call sites; consider extracting one shared 'card title' helper so future renderers don't repeat the omission.
BUG-020 | High | Frontend / Join Requests — Stored XSS | Requester name built from firstName/lastName and inserted unescaped. | frontend/placeonix-hub-portal.html:3630 (renderJoinRequests) | Name is concatenated from user-supplied firstName/lastName without escHtml(). | Apply escHtml() to the constructed name string before insertion.
BUG-021 | High | CORS Configuration | CORS origin whitelist defaults to '*' while credentials:true is also set. | placeonix-hub-backend/src/app.js:27-38 | The origin callback treats whitelist.includes('*') as blanket approval; combined with credentials:true this is overly permissive if CLIENT_URL is ever left at its documented wildcard default. | In production, reject a '*' CLIENT_URL at startup (fail fast with a clear error) and require an explicit comma-separated origin list; keep '*' allowed only when NODE_ENV==='development'.
BUG-022 | High | Payments — Validation | Every money-handling route has zero input validation. | placeonix-hub-backend/src/routes/paymentRoutes.js:9 (pay), 13 (record), 14 (update), 15 (refund) | No express-validator rules attached; amount/method/enrollmentId/transactionId are trusted as submitted. | Add express-validator chains (amount is a positive number, method is one of an allowed enum, enrollmentId is a valid Mongo ObjectId) plus the validate middleware to all four routes.
BUG-023 | High | Services / Notifications | Notification-send failures are silently swallowed with no surfaced error. | placeonix-hub-backend/src/services/notificationService.js:10-14 (send) | Errors from Notification.notify() are caught, logged via logger.error, and the function returns undefined; every caller ignores the return value. | Either propagate a boolean/result the caller can react to, or add a monitored failure counter/alert so repeated notification failures are visible to admins, not just buried in logs.
BUG-024 | Medium | Auth | user.save() in the token-issuing helper is not awaited. | placeonix-hub-backend/src/controllers/authController.js:19 (sendTokens) | user.save({validateBeforeSave:false}) is called without await, creating a possible unhandled promise rejection / race with the response being sent before the refresh token is persisted. | Add await before user.save(...), and make sendTokens an async function awaited by its callers.
BUG-025 | Medium | Courses — Validation & mass assignment | Course update/module endpoints accept unvalidated, unfiltered request bodies. | placeonix-hub-backend/src/controllers/courseController.js:63-71 (updateCourse), 85-98 (addModule), 103-115 (updateModule, Object.assign), 167-181 (updateTopic, Object.assign) | No express-validator rules on these routes; Object.assign(mod, req.body) / findByIdAndUpdate(req.body) copy arbitrary keys including protected fields like createdBy or enrollmentCount. | Add validator chains for each route and replace Object.assign(target, req.body) with an explicit field whitelist, e.g. const {title,description,order} = req.body; Object.assign(target, {title,description,order}).
BUG-026 | Medium | Courses — Unhandled input shape | reorderModules throws a 500 instead of a 400 on malformed input. | placeonix-hub-backend/src/controllers/courseController.js:132-145 (reorderModules) | req.body.order is used directly in .forEach with no check it's an array; if undefined/non-array this throws 'order.forEach is not a function'. | Validate req.body.order is a non-empty array (express-validator isArray()) before the loop, and return a 400 AppError if not.
BUG-027 | Medium | Batches — Validation & mass assignment | Batch create/update endpoints have no validation and allow overwriting protected fields. | placeonix-hub-backend/src/controllers/batchController.js:69-82 (createBatch), 86-94 (updateBatch) | req.body reaches Batch.create / findByIdAndUpdate unchecked beyond an ad-hoc capacity check. | Add validator chains (name, capacity as positive int, valid startDate/endDate, valid course/mentor ObjectIds) and whitelist updatable fields to exclude createdBy/enrolledCount/mentor from direct overwrite.
BUG-028 | Medium | Batches — Race condition | Concurrent enroll requests can push a batch's enrolledCount past its capacity. | placeonix-hub-backend/src/controllers/batchController.js:113-143 (enrollStudent) | The capacity check (line 118) and the enrolledCount += 1 / save() (lines 137-138) are not atomic — two simultaneous requests can both pass the check before either increments. | Replace the check-then-save with a single atomic update: Batch.findOneAndUpdate({_id, enrolledCount:{$lt: capacity}}, {$inc:{enrolledCount:1}}), and treat a null result as 'batch full'.
BUG-029 | Medium | Sessions — Validation & mass assignment | Session create/update endpoints have no validation and allow overwriting protected fields. | placeonix-hub-backend/src/controllers/sessionController.js:78-93 (createSession), 97-104 (updateSession) | req.body spread directly into Session.create / findByIdAndUpdate with only a batch-existence check. | Add validator chains and whitelist updatable fields (exclude instructor, batch, createdBy from PATCH).
BUG-030 | Medium | Sessions — Unvalidated fields | Session-completion fields are written without validation. | placeonix-hub-backend/src/controllers/sessionController.js:132-145 (completeSession) | req.body.notes/homework/recordingUrl written unchecked, no URL-format validation on recordingUrl. | Add a URL-format validator (isURL()) for recordingUrl and a max-length check for notes/homework.
BUG-031 | Medium | Attendance — Unscoped mentor reads | Any mentor can view attendance for any batch or any student, not only their own. | placeonix-hub-backend/src/controllers/attendanceController.js:191-219 (getBatchAttendance), 255-277 (getStudentAttendance) | No check that batch.mentor === req.user._id (markAttendance at line 128 already does this correctly — the pattern just isn't applied consistently). | Reuse the same ownership check already present in markAttendance for these two read endpoints.
BUG-032 | Medium | Placements — Validation & unfiltered writes | Placement drive and application endpoints accept unvalidated bodies; updateDrive skips schema validation. | placeonix-hub-backend/src/controllers/placementController.js:47-50 (createDrive), 54-58 (updateDrive, missing runValidators:true), 98-118 (updateApplication, Object.assign) | No express-validator rules; updateDrive's findByIdAndUpdate omits runValidators so Mongoose schema rules are skipped on update; updateApplication's Object.assign(app, req.body) lets a caller set placedAt/history/finalOffer directly, bypassing the intended status-transition logic. | Add validators, pass {runValidators:true, new:true} to updateDrive's findByIdAndUpdate, and replace the Object.assign in updateApplication with an explicit status-transition function that validates req.body.status against the allowed enum.
BUG-033 | Medium | Placements — Analytics performance | Placement analytics loads entire collections into memory instead of aggregating in MongoDB. | placeonix-hub-backend/src/controllers/placementController.js:122-171 (placementAnalytics) | PlacementDrive.find() and Enrollment.find().populate(...) pull full collections, then iterate/reduce in JavaScript. | Rewrite using a MongoDB aggregation pipeline ($group/$lookup) so the reduction happens in the database, not in Node.
BUG-034 | Medium | Announcements — Validation | Announcement create/update endpoints have no input validation. | placeonix-hub-backend/src/controllers/announcementController.js:54-83 (createAnnouncement), 87-91 (updateAnnouncement) | No express-validator rules attached, unlike leadController/reviewController which do validate their create routes. | Add validator chains for title (required, max length), body (required), and audience (must be one of the allowed enum values).
BUG-035 | Medium | Announcements — Swallowed error | Notification fan-out failure for a new announcement is silently dropped. | placeonix-hub-backend/src/controllers/announcementController.js:78-80 | catch (e) { /* best-effort */ } with no logging. | At minimum log the error via the shared logger so failures are visible; consider a retry queue for notification fan-out.
BUG-036 | Medium | Leads — Validation | Lead update endpoint has no input validation. | placeonix-hub-backend/src/controllers/leadController.js:48-56 (updateLead) | Raw req.body spread into findByIdAndUpdate with no validator chain (unlike createLead's partial validation). | Add a validator chain mirroring createLead's, plus restrict which fields updateLead may change (status/assignedTo/notes only, not email/phone re-assignment without review).
BUG-037 | Medium | Leads — Empty note | Lead notes can be saved empty/undefined. | placeonix-hub-backend/src/controllers/leadController.js:60-67 (addNote) | No check that req.body.text is present/non-empty before pushing into lead.notes. | Add a check (or express-validator notEmpty()) before pushing the note.
BUG-038 | Medium | Reviews — Retargeting | A student can change which mentor/course a review targets after creation. | placeonix-hub-backend/src/controllers/reviewController.js:59-69 (updateReview) | No validator on PATCH /:id (unlike POST / which validates targetType/target/rating); Object.assign(review, req.body) lets targetType/target be overwritten post-creation. | Add a validator chain to PATCH restricting which fields are editable (rating, comment only) — exclude targetType/target from the whitelist entirely.
BUG-039 | Medium | Resources — Validation & unbounded list | Resource update has no validation; resource listing has no upper bound on page size. | placeonix-hub-backend/src/controllers/resourceController.js:11 (listResources), 96 (updateResource); routes/resourceRoutes.js:19 | updateResource forwards req.body unfiltered into findByIdAndUpdate; listResources' limit query param has no cap, so ?limit=999999 returns the full collection. | Add a validator + field whitelist to updateResource (exclude uploadedBy/accessLevel from client-settable fields), and clamp limit to a sane maximum (e.g. Math.min(limit, 100)) server-side.
BUG-040 | Medium | Companies / Alumni / Office Hours / Mock Interviews — Validation | Create/update endpoints across these four modules have no input validation. | companyRoutes.js:9-11, alumniRoutes.js:9-10, officeHourRoutes.js:9-10, mockInterviewRoutes.js:9-10 | None of these route groups attach express-validator chains before their controllers write to the database. | Add validator chains per model's required fields (Company: name/website; Alumni: name/batch/company; OfficeHourSlot: startTime/endTime as valid dates; MockInterview: student/interviewer/scheduledAt) and wire the shared validate middleware.
BUG-041 | Medium | Mock Interviews — Ownership on delete | Any mentor can delete another mentor's mock interview record. | placeonix-hub-backend/src/controllers/mockInterviewController.js:85-89 (deleteMock) | Same missing-ownership pattern as BUG-011, specific to delete. | Add the interviewer-ownership check before permitting delete.
BUG-042 | Medium | Users — Performance (N+1) | Leaderboard computes each student's stats with two separate awaited queries inside a loop. | placeonix-hub-backend/src/controllers/userController.js:229-250 (leaderboard) | students.map(async ...) issues 2 queries per student instead of one batched/aggregated query. | Replace with a single aggregation pipeline (or two bulk queries keyed by studentId, joined in memory) instead of per-student round trips.
BUG-043 | Medium | Users — Validation gap on profile update | Students can set arbitrary profile subfields via PATCH /users/:id. | placeonix-hub-backend/src/routes/userRoutes.js:36; controllers/userController.js | ownerOrAdmin middleware correctly restricts *who* can call this, but the controller only strips password/role — it doesn't whitelist which of the remaining fields (status, createdBy, studentProfile.*) are legitimately student-editable. | Define an explicit editable-fields whitelist per role (e.g. student may edit firstName/lastName/phone/bio/studentProfile.{degree,college,skills,resume,linkedIn,github,portfolio} only) and filter req.body against it before the update.
BUG-044 | Medium | Data Integrity — No cascade delete | Deleting a Course/Batch leaves dependent records pointing at a dead ID. | All files in placeonix-hub-backend/src/models/ (no pre('remove')/pre('findOneAndDelete') hooks found anywhere) | Course -> Batch -> Enrollment -> Session -> Assignment -> Attendance -> Certificate are all bare ObjectId refs with no cleanup logic on delete. | Either add pre-delete middleware per model to cascade-delete or cascade-flag dependents, or switch to soft-delete (an active:false/deletedAt flag) and filter all reads by it, which is generally safer for this kind of interlinked academic data.
BUG-045 | Medium | Frontend — Demo data shipped in production | A large hardcoded demo dataset and full API-mocking layer ship inside the production bundle. | frontend/placeonix-hub-portal.html:880-1002 (_DEMO_USERS, _DEMO_COURSES, etc., and _demoResponse()) | apiFetch() silently branches to fabricated data whenever _demoMode is true, and doLogin() (line 1311) can auto-activate this mode heuristically on a perceived backend outage, using a hardcoded password check. | Move demo data/mock layer behind a build-time flag or a separate demo-only bundle so it never ships to the production URL; if a live demo mode is a deliberate product feature, show a persistent, unmissable banner whenever it's active rather than auto-activating silently.
BUG-046 | Medium | Frontend — UX inconsistency | Two flows fall back to native prompt()/alert() instead of the app's own modal/toast pattern. | frontend/placeonix-hub-portal.html:2801 (submitAssignment), 2930-2938 (applyDrive) | These are the only two places in the SPA using browser-native dialogs; every other flow uses formModal()/toast(). | Rebuild both flows using the existing formModal() + toast() helpers already used elsewhere in the file for consistency.
BUG-047 | Medium | Frontend — Inconsistent error handling | Dashboard-load functions handle partial API failures inconsistently within the same function. | frontend/placeonix-hub-portal.html:1502 (renderCalendar), 2009 (renderStudentDash) | Some parallel fetches are caught into empty arrays (silent empty state), others are left to throw to the page-level error handler, within the same function. | Pick one consistent pattern per page — either all-fail-silently-to-empty-state, or all-throw-to-a-visible-error-banner — and apply it uniformly across each page's fetch calls.
BUG-048 | Medium | Frontend — Swallowed parse errors | Malformed/non-JSON API responses are silently treated as an empty success. | frontend/placeonix-hub-portal.html:1061 (apiFetch) | JSON parse errors inside apiFetch are caught and coerced to {} instead of surfacing as a failure. | Re-throw (or return an explicit {success:false, error:'invalid response'}) on a JSON parse failure instead of masking it as {}.
BUG-049 | Medium | Frontend — Incomplete escaping | Feedback input is only quote-escaped, not fully HTML-escaped. | frontend/placeonix-hub-portal.html:3241 | Value is passed through .replace(/"/g,'&quot;') only, leaving <, >, & unescaped in an attribute context. | Replace the ad-hoc .replace() call with the shared escHtml() helper used elsewhere.
BUG-050 | Medium | Services — Cron job resilience | A single failure inside a cron job's student loop aborts the remaining loop for that run. | placeonix-hub-backend/src/services/cronService.js:26-30 (feeReminderJob), 46-60 (attendanceWarningJob), 139-152 (assignmentReminderJob) | Each job wraps its entire per-student loop in one outer try/catch, so one thrown error skips every remaining student in that run. | Move the try/catch inside the loop body (per-student), logging and continuing on individual failures instead of aborting the whole batch.
BUG-051 | Low | Reviews — Query pattern inconsistency | deleteReview fetches the document before checking ownership instead of combining both in one query. | placeonix-hub-backend/src/controllers/reviewController.js:73-86 | Review.findOne({_id:...}) is called first, then ownership is checked separately, unlike updateReview which combines the ownership filter into the query directly. | Combine the ownership condition into the initial query filter (as updateReview already does) for consistency — functional today, but worth aligning the pattern.
BUG-052 | Low | Uploads — MIME allow-list not independently verified | Upload routes delegate file-type checking to uploadService with no visible allow-list at the route layer. | placeonix-hub-backend/src/routes/uploadRoutes.js:24-43 | No server-side MIME/extension allow-list visible in the route file itself; relies entirely on uploadService's internal checks. | Confirm uploadService enforces an explicit MIME + extension allow-list (not just a deny-list) for every upload route, and add a test asserting a disallowed file type is rejected with 400.
BUG-053 | Low | Data Model — Weak referencing | Alumni course/batch fields are free-text strings instead of ObjectId references. | placeonix-hub-backend/src/models/Alumni.js:8-9 | Unlike Enrollment, Certificate, Assignment, and Session, which all reference Course/Batch by ObjectId, Alumni stores these as plain strings. | Migrate to ref: 'Course' / ref: 'Batch' ObjectId fields with a data-migration script to backfill existing records by name match.
BUG-054 | Low | Data Model — Missing audit field | Company records can be created with no audit trail of who created them. | placeonix-hub-backend/src/models/Company.js:14 | createdBy is not marked required, unlike the equivalent field on Course/Batch/Session/Assignment/Announcement. | Add required:true to createdBy and backfill or default existing records.
BUG-055 | Low | Data Model — Missing index | bookedBy on OfficeHourSlot is not indexed despite being used to look up a student's bookings. | placeonix-hub-backend/src/models/OfficeHourSlot.js:5 | Only mentor is indexed; the reverse lookup (a student's own bookings) will do a collection scan as data grows. | Add an index on bookedBy alongside the existing mentor index.
BUG-056 | Low | Data Model — Duplicate indexes | Several fields have duplicate index declarations, producing boot-time Mongoose warnings. | placeonix-hub-backend/src/models/User.js (status, studentProfile.enrollmentId), Course.js (slug) | Each field is declared with both index:true in the schema definition and again via schema.index() — harmless but wasteful and noisy in logs. | Remove the duplicate declaration for each field, keeping only one (index:true inline, or schema.index() if compound indexing is needed).
BUG-057 | Low | Services — Logging inconsistency | File-delete failures are logged with console.error instead of the shared logger, and swallowed. | placeonix-hub-backend/src/services/uploadService.js:85-88 (deleteFile) | Bypasses the Winston logger used everywhere else in the file/codebase; caller never learns deletion failed. | Use the shared logger.error(...) for consistency, and propagate a boolean/result so callers (e.g. avatar-replace flow) can react to a failed cleanup.
BUG-058 | Low | Services — Hardcoded values | Email templates contain hardcoded sender name and a hardcoded phone number. | placeonix-hub-backend/src/services/emailService.js:37 (fallback sender), 155 (lead-confirmation phone number) | 'Placeonix <noreply@placeonix.in>' and '+91 98765 43210' are hardcoded directly in template strings. | Move both into environment/config variables (EMAIL_FROM already exists for the first; add a CONTACT_PHONE constant for the second) so they can change without a code deploy.
BUG-059 | Low | Frontend — Accessibility | Primary click targets (sidebar nav, quick links, course rows) are unreachable by keyboard or screen reader. | frontend/placeonix-hub-portal.html:1389 (sidebar), 2877 (quick links), 2107 (course rows) | These are plain <div onclick=...> elements with no role, tabindex, or keyboard handler. | Convert to real <button>/<a> elements where possible, or add role="button" tabindex="0" plus a keydown handler for Enter/Space to each.
BUG-060 | Low | Frontend — Accessibility | Password-visibility toggle's aria-label is never updated after state changes. | frontend/placeonix-hub-portal.html:779 (markup), 1248-1258 (togglePass) | aria-label="Show password" is set once in markup and never flips to "Hide password" when toggled. | Update the aria-label attribute inside togglePass() to reflect the current state.
BUG-061 | Low | Frontend — Accessibility | CSV import file input has no associated label. | frontend/placeonix-hub-portal.html:3075 (#impFile) | <input type="file" id="impFile"> has no <label for="impFile">. | Add a proper <label for="impFile"> (visually hidden if needed) for screen-reader users.
BUG-062 | Low | Frontend — Accessibility | Profile page form labels are not associated with their inputs. | frontend/placeonix-hub-portal.html:3440-3453 | Labels lack a for attribute tying them to the corresponding input/textarea id, unlike formModal()'s generated fields (line 4185). | Add matching id/for pairs to every profile-page label/input, following the pattern already used in formModal().
BUG-063 | Low | Frontend — Missing client-side validation | URL-type fields are marked required but never format-validated. | frontend/placeonix-hub-portal.html:1608 (company website), 1799-1801 (alumni photo/LinkedIn), 3584/3599 (meeting link), 3770 (resource URL) | required only checks non-empty; no pattern/type=url validation catches a malformed value before submit. | Add type="url" (or a regex pattern attribute) to these inputs for basic client-side format validation, in addition to required.
BUG-064 | Low | Frontend — Inconsistent validation UX | Attendance-save validation shows a plain inline message instead of the app's field-level error pattern. | frontend/placeonix-hub-portal.html:2770 (saveAttendance) | Uses a generic inline text message rather than the field-level error styling used by formModal() (lines 4199, 4203). | Reuse the formModal() field-error pattern for consistency with the rest of the app.
BUG-065 | Low | Frontend — Security boundary clarity | Role-based UI hiding is implemented purely client-side in over a dozen places. | frontend/placeonix-hub-portal.html: 1380, 1662, 1771, 1830, 2570, 2574, 2794, 2875, 3410, 3447, 3686, 3720 | These sites hide buttons/sections via role==='admin'¦¦role==='mentor' checks in JS only — cosmetic, not a security boundary. | No frontend change strictly required, but every one of these must have a matching server-side check (see BUG-007 through BUG-014 for the confirmed gaps) — client hiding should be treated as UX polish only, never as access control.
BUG-066 | Low | Frontend — Dead code | Unused calendar-row-building logic left in the codebase. | frontend/placeonix-hub-portal.html:2607-2626 (calRows) | Built via a string-split loop but never used; a comment nearby confirms it's leftover from replaced logic. | Delete the dead calRows block and its comment.
BUG-067 | Low | Frontend — Dead code | reviewAssignment(id) ignores its parameter and appears superseded. | frontend/placeonix-hub-portal.html:2816 | Just calls showPage('assignments') regardless of id; mentorAssignmentCard actually uses viewSubmissions() (line 3155) instead. | Remove reviewAssignment() if confirmed unused, or wire it to actually open the specific assignment if it was meant to.
BUG-068 | Low | Frontend — Dead code | A no-op variable assignment in convertLead() always evaluates to null. | frontend/placeonix-hub-portal.html:3311 | var l = _leadsCache.find ? null : null; is a leftover statement that always resolves to null and is unused — the real lookup happens on the next line. | Delete this line.
BUG-069 | Low | Frontend — Debug logging left in | A debug console.warn is left active in production code. | frontend/placeonix-hub-portal.html:3114 | console.warn('Import failures:...') is not gated behind any debug flag. | Remove it, or gate it behind a DEBUG flag checked at build/runtime.
BUG-070 | Low | Frontend — Duplicated logic | The meetingLink-or-fallback + guarded-onclick pattern is duplicated at four call sites instead of shared. | frontend/placeonix-hub-portal.html:1989, 2035, 2338, 2400 | Same meetingLink¦¦'#' plus guard logic repeated four times instead of extracted into a helper. | Extract a small shared helper, e.g. joinLinkAttrs(meetingLink), and call it from all four sites.
BUG-071 | Low | Frontend — Missing empty state | Join-request history section renders nothing when there are no resolved requests. | frontend/placeonix-hub-portal.html:3640 (renderJoinRequests, resolved history) | No explicit 'No history yet' message, inconsistent with other lists in the app (e.g. line 2117) that do show one. | Add the same empty-state pattern used elsewhere for the resolved/history section.

## Summary
Placeonix Hub — Dashboard Audit: Bug Tracker Summary By Mohan Karthikeya
Severity | Count
Critical | 6
High | 17
Medium | 27
Low | 21
Total | 71